## Slide 1: Remembering the Trojans
Plaza Middle School 2013 Graduating Class

## Slide 3: Here is the Plan…

## Slide 4: Introduction
The purpose of our Design project is to commemorate the 2013 Plaza Middle School senior class.

## Slide 5: How?
Have the 8th grade class create designed ceiling tiles for Plaza
The Entire 8th grade (MYP and Plaza)
The tiles will be the ones in the main office hallway.
We will have a day for the Cambridge students to design theirs together
And another day for the other 8th grade teams

## Slide 6: Theme
The theme of our project is remembrance. We plan to use the ceiling as way to leave our mark on Plaza, and have future students remember our achievements. The tiles would represent our achievements and experiences at Plaza as well as how Plaza has shaped the people we are today.

## Slide 7: Prior Approvals
We have discussed the project with Mrs. Horning and Mrs. Krzewinski. Also we have an appointment for final approval set up with Dr. Hoyle. We still need approval from the custodial staff, and approval from Art teachers for material purposes.

## Slide 8: Materials/Cost
What do we need:
Crayola Oil Pastels 28 color set ($3.00 per box)
Tempera paint ($3.00 per bottle)
Paint Brushes (Supplied)

## Slide 9: Work Schedule
April 26th/29th - We will be preparing for the constructing days by confirming the availability of the supplies. We will modify our design if possible to suit all the creators in our grade. Our designs will also be modified based on suggestions by our fellow classmates
June 6th – 11th We will have finalized days for the other teams to create their tiles, we will have all of our designs completed and supplies ready for creation. We will also have all of the permission slips for students to stay after school returned, just so that we can approximate all the people who are going to be present.
June 12th – the Cambridge team will stay after school to construct the tiles.
June 14th – This day will be the unveiling of the brand new main hallway.

## Slide 10: Roles for Students
On the day of June 12th the students will be:
Constructing their tile designs (3 people per tile)
After each group is finished we will have another group put the tiles in a place to dry
In the morning of the last day of school, we will have a group of students placing the tiles back in the ceiling. (Based on approval of Mr. Woodies and Dr. Hoyle)

## Slide 11: Design Outline: